PROJECT PHOENIX

Hardhat Enterprises - Cyber Security Stream

Authentication & RBAC Security Review

Part B - Sprint 1 · Complete 8-Week Work Plan

Sub-Team: Authentication & RBAC Review

Lead: Himanshu

Members: Saad · Muath · Divjot Singh

Prepared by Himanshu - Sub-Team Lead

Version 2.0  ·  Full team (4 members)

# Contents

Contents	1

1. Executive Summary	1

Objectives (what 'done' means for the whole project)	1

2. Scope	1

3. Team & Responsibilities	1

4. Methodology & Standards	1

Standards we align to	1

Severity rating	1

Definition of Done (per finding)	1

5. Known-Issue Baseline	1

6. Tools We Will Use	1

7. Weekly Work Plan	1

Week 1 - Kick-off, Environment & Reconnaissance	1

Week 2 - Baseline Verification, Dependency & Config Audit	1

Week 3 - Authentication Deep-Dive: Tokens & Login	1

Week 4 - Registration, Password Reset & Input Handling	1

Week 5 - RBAC Model & Authorization Enforcement	1

Week 6 - Privilege Escalation & Bypass Testing	1

Week 7 - Consolidation, Severity & Remediation	1

Week 8 - Final Report & Showcase	1

8. Progress Tracking & Governance	1

Weekly sync (standing agenda)	1

Risks & Mitigations	1

# 1. Executive Summary

Project Phoenix is a disaster-response platform, built with Hardhat Enterprises, that detects cyber threats scams, phishing, and misinformation which surge during natural disasters. The backend is a set of microservices (API Gateway, User Service, Data-Ingestion, Storage, Notification) communicating over gRPC, backed by PostgreSQL (Supabase), RabbitMQ, and Redis.

Our sub-team is responsible for a complete security review of Authentication and Role-Based Access Control (RBAC) how Phoenix verifies who a user is, and how it enforces what each user is allowed to do. The objective for this trimester is to fully complete this review: identify every weakness, prove it with evidence, rate it, and recommend a concrete fix, so the work can be closed out and handed over cleanly.

This document is the master plan. It defines scope, team roles, methodology, standards, a known-issue baseline, and a detailed week-by-week schedule for all 8 weeks with owners, granular checklists, deliverables, and acceptance criteria. It is written to be thorough and defensible the depth is intentional, so both the quality and completeness of our work are evidenced.

## Objectives (what 'done' means for the whole project)

- Every authentication and RBAC weakness in the current backend is found, proven, and documented.

- Each finding has reproducible steps, evidence, a severity rating, and a remediation recommendation.

- A professional final vulnerability report is delivered, matching the Part A format.

- A showcase presentation and live demo are prepared and rehearsed.

- A clean hand-off pack (fixes + re-test checklist) is produced so nothing is left open.

# 2. Scope

| Area | Detail |
| --- | --- |
| IN SCOPE | Login, logout, token refresh, registration, and password-reset flows; JWT generation and validation; session handling; password storage; RBAC middleware; role definitions; route-level authorization; horizontal and vertical privilege escalation; direct-service (gRPC) access bypass; and auth-related dependency and configuration hygiene. |
| OUT OF SCOPE | Non-auth business logic of the Threat, Hazard, Storage, and Notification services (owned by other sub-teams); frontend UI; ML / AI model internals; and general infrastructure hardening beyond the authentication surface. |
| COORDINATION | Jessica's 'Enhance API Security' sub-team overlaps on rate limiting, headers, and the security middleware. A written scope boundary is agreed in Week 1 and reviewed weekly. Any backend change by other teams triggers a fresh pull before we continue testing. |

# 3. Team & Responsibilities

The sub-team has four members. Work is divided into four clear streams so each person owns an area end-to-end, with the lead coordinating and handling the token-security core.

| Member | Stream | Responsibilities |
| --- | --- | --- |
| Himanshu (Lead) | Token security + coordination | JWT and session token analysis, weak-secret testing, overall planning, weekly syncs, consolidating findings, final report and showcase. Reviews and signs off every finding. |
| Saad | Login, sign-up & password reset | Endpoint mapping, login rate limiting / brute-force, username enumeration, registration abuse, password-reset flow, input validation. |
| Muath | Roles & privilege escalation | Role definitions, RBAC middleware logic, the role×route access matrix, and horizontal & vertical privilege-escalation testing. |
| Divjot Singh | Dependency & configuration audit | npm vulnerability audit across services, .env and docker-compose review, secrets-in-logs check, and secure-configuration recommendations. |

Note:  With four members we cover more ground in parallel. Divjot's dependency/configuration stream is largely independent, so it can run alongside the login and RBAC work without blocking anyone.

# 4. Methodology & Standards

Every area is reviewed with three complementary techniques, so findings are solid and defensible:

- Code review  read the actual source (routes, controllers, middleware, services) in the User Service and API Gateway, rather than inferring behaviour from the outside.

- Dynamic testing  exercise every endpoint with Postman and curl, plus targeted tools (Burp Suite, sqlmap, Hydra, custom scripts, grpcurl) as appropriate.

- Configuration & dependency audit  inspect .env, docker-compose, startup logs, and npm audit output for weak secrets, exposed credentials, and vulnerable packages.

## Standards we align to

Findings are framed against recognised industry standards, so the work is done to a professional bar and is easy to defend:

- OWASP Top 10 (2021)  A01 Broken Access Control, A02 Cryptographic Failures, A07 Identification & Authentication Failures.

- OWASP ASVS v4  Chapter 2 (Authentication), Chapter 3 (Session Management), Chapter 4 (Access Control).

- OWASP Cheat Sheets  Authentication, JWT, Session Management, Password Storage.

- CWE identifiers per finding (e.g., CWE-798 hard-coded credentials, CWE-521 weak password requirements, CWE-639 authorization bypass, CWE-307 improper restriction of excessive authentication attempts).

## Severity rating

| Severity | Meaning |
| --- | --- |
| Critical | Directly exploitable; leads to full compromise or admin takeover. Fix immediately. |
| High | Exploitable with modest effort; significant data or privilege exposure. |
| Medium | Requires specific conditions or partial exposure; fix this sprint. |
| Low | Hardening / best-practice gap; limited direct impact. |

## Definition of Done (per finding)

- Reproducible steps documented (request, payload, response).

- Evidence captured (screenshot / raw HTTP / log excerpt).

- Root cause located in code where possible (file + line).

- Severity assigned with an OWASP / CWE reference.

- Remediation recommendation written.

- Reviewed and signed off by the sub-team lead.

# 5. Known-Issue Baseline

These items are carried from Part A or observed during setup. They must be re-verified against the current backend, then formally logged. They also seed the deeper testing. Ownership is mapped to the responsible stream.

| ID | Observation | Severity | Owner / re-check |
| --- | --- | --- | --- |
| B-01 | No rate limiting on the login endpoint (brute-force possible). | High | Saad - Week 3 |
| B-02 | Client-supplied 'role' field on registration allowed admin self-provisioning. | Critical | Muath - Week 4 |
| B-03 | Unauthenticated data-ingestion endpoint. | High | Muath / Himanshu - Week 6 |
| B-04 | Weak JWT secrets in config (e.g. AUTH_JWT_SECRET=secret123, refresh secret=refreshsecret123). | Critical | Himanshu - Week 3 |
| B-05 | 11 npm vulnerabilities per service (1 low, 5 moderate, 5 high) outdated dependencies. | High | Divjot - Week 2 |
| B-06 | DB credentials & JWTs printed in plaintext service logs. | Medium | Divjot - Week 2/5 |

# 6. Tools We Will Use

The toolset below covers the whole engagement. Most are already available from Part A; a few (Hydra, hashcat, grpcurl) may need installing.

| Purpose | Tools |
| --- | --- |
| Run the system | Docker Desktop, Git / GitHub, VS Code |
| Inspect login tokens (JWT) | jwt.io (decode), hashcat or John the Ripper (crack weak secret), Postman (obtain tokens) |
| Login & brute-force testing | Burp Suite (Intruder), Hydra, Part A brute_force_test.py script |
| Sign-up & input testing | sqlmap (injection), Burp Repeater (edit requests), Postman (malformed input) |
| RBAC & privilege escalation | Postman / Burp (per-role route testing), grpcurl (direct gRPC / gateway-bypass) |
| Dependency & config audit | npm audit (built-in), OWASP ZAP (automated scan backup) |
| Reporting & evidence | Word / Google Docs, screenshots, Burp saved requests/responses |

# 7. Weekly Work Plan

Eight weeks, each with owners for all four members, an exhaustive checklist, and defined deliverables with acceptance criteria. The checklists are intentionally granular so the depth and completeness of the work are evidenced.

# Week 1  Kick-off, Environment & Reconnaissance

Get the whole team running the backend, agree tooling and scope, and map the authentication surface before testing.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Himanshu | Onboard the team (incl. Divjot); write the 1-page setup guide; agree written scope boundary with Jessica's API-security team; set up the shared workspace and findings register. | Setup guide + scope MoU + register |
| Saad | Map every authentication endpoint from the route/controller files: method, path, inputs, outputs. Include the password-reset flow. | Endpoint inventory |
| Muath | Read the RBAC middleware and role constant; list all roles and how identity is attached and checked. | Roles & middleware notes |
| Divjot | Set up the backend; get familiar with the project structure; prepare the environment for the dependency/config audit (npm, access to .env & compose). | Environment ready + structure notes |

### Detailed checklist  every item to cover

- Backend builds and all services report Up/Healthy on every member's machine.

- Health check (GET /health on the gateway) returns success for everyone.

- Shared workspace created for evidence, screenshots, and the findings register.

- Findings register template created (ID, area, description, steps, severity, OWASP/CWE, status, owner).

- Auth endpoint inventory complete: login, logout, refresh, register, and password reset (if present).

- Confirm whether a real backend password-reset route exists (frontend ForgotPassword page was spotted).

- Roles confirmed: Admin, Analyst, End User, Ingestion Service.

- gRPC surface noted: which auth logic sits in User Service vs API Gateway.

- Tooling installed & agreed across the team (Postman, Burp, sqlmap, jwt.io, npm audit; plus Hydra/grpcurl where needed).

- Test accounts identified for each role, or requested from the backend lead.

  - Confirm the canonical stable branch (dev) with the backend co-lead.

  - Written scope boundary agreed with Jessica's team (who owns rate limiting / middleware).

### Deliverables & Acceptance

- Setup guide - one page; boots the backend from scratch.

- Endpoint inventory - all auth endpoints with inputs/outputs.

- Roles & middleware notes - how RBAC is wired.

- Findings register - structured and ready to fill from Week 2.

# Week 2  Baseline Verification, Dependency & Config Audit

Re-verify every Part A issue on the current code, and complete the full dependency and configuration hygiene pass.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Divjot | Run npm audit per service; catalogue the 11 vulnerabilities (name, CVE, severity, fixed-in version). Verify B-05. Review .env and docker-compose for weak secrets and unsafe defaults; check startup logs for secret leakage (B-06). | Dependency + config audit report |
| Himanshu | Re-verify B-04 (weak JWT secrets) and support Divjot on B-06 (secrets in logs); capture evidence. | B-04 verified |
| Saad | Re-verify B-01 (login rate limiting) at a high level and refine the endpoint inventory with request/response samples. | B-01 status + samples |
| Muath | Walk an authenticated request end-to-end (gateway → middleware → user-service → DB) and document the trust boundaries. | Auth data-flow diagram |

### Detailed checklist  every item to cover

- Each Part A baseline item (B-01…B-06) re-tested and marked Confirmed / Fixed / Changed on the current build.

- npm audit output saved for api-gateway, user-service, data-ingestion, storage, notification.

- Each vulnerable package mapped to CVE and 'fixed in' version.

- .env reviewed line-by-line for weak values and secrets that shouldn't be committed.

- docker-compose environment reviewed for hard-coded credentials and unsafe defaults.

- Startup logs checked for secrets (DB URL, tokens, dotenvx output).

- .gitignore confirmed to exclude .env / .env.docker (no secret leakage to Git).

- NODE_ENV recorded per service (production vs development); any debug flags noted.

- Weak JWT secrets (secret123 / refreshsecret123) confirmed and logged as B-04.

### Deliverables & Acceptance

- Dependency audit - full CVE table across all services with fix versions.

- Config audit note - .env / compose / logs findings with severities.

- Baseline verification table - Part A findings with current status + evidence.

# Week 3  Authentication Deep-Dive: Tokens & Login

The core of the review. Examine JWT issuance/validation and login security in depth.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Himanshu | JWT deep-dive: decode access & refresh tokens; inspect algorithm, claims, expiry, signature verification, and secret strength (B-04). Attempt to forge a token using the guessed secret. | JWT analysis + forge test |
| Saad | Login security: test rate limiting / lockout (B-01), brute-force resistance, and username enumeration via error/timing differences. | Login test results |
| Muath | Session & logout: verify logout truly invalidates tokens; test token reuse after logout; check refresh-token rotation and the logout/:userId parameter. | Session/logout results |
| Divjot | Finalise the dependency/config report; begin drafting remediation for weak secrets and vulnerable packages. | Draft config remediation |

### Detailed checklist  every item to cover

- Decode a real access token: confirm algorithm (HS256), header, and payload claims (user_id, role, iat, exp).

- Verify the server validates the signature (test a tampered token; test alg:none).

- Measure access vs refresh token lifetime; flag long-lived access tokens.

- Test weak-secret impact: attempt to crack/guess the HS256 secret (secret123).

- Forge a token re-signed with the guessed secret and an elevated 'role'; attempt to use it.

- Brute-force login (N failed attempts): is there rate limiting, lockout, or CAPTCHA? (B-01)

- Username enumeration: compare responses/timing for valid vs invalid usernames.

- Confirm the password is never returned in any response or token.

- Logout: replay old access & refresh tokens after logout - should be rejected.

- logout/:userId: test whether one user can log out another by changing the id in the URL.

- Refresh flow: is a used refresh token invalidated (rotation)? Can it be replayed?

- Check handling of missing 'exp'/'nbf' and clock-skew tolerance.

### Deliverables & Acceptance

- JWT analysis - token structure, weaknesses, and forge-attempt result.

- Login security findings - rate limiting / enumeration results with evidence.

- Session findings - logout/refresh/logout-by-id behaviour with steps.

# Week 4  Registration, Password Reset & Input Handling

Verify the sign-up and reset flows can't be abused (especially the Part A role escalation), and that auth inputs are validated.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Muath | Re-test B-02: attempt to register with a client-supplied 'role' to self-provision admin/analyst on the current code. | B-02 verification |
| Saad | Password-reset review: how reset tokens/links are generated, their strength, expiry, and single-use; plus input validation and mass-assignment on auth endpoints. | Reset + input findings |
| Himanshu | Password policy & storage: minimum length/complexity, hashing algorithm & work factor; injection testing (SQLi) on login/register. | Password + injection findings |
| Divjot | Cross-check dependency findings against the auth code paths (are vulnerable packages actually used in auth?); tidy the audit evidence. | Dependency impact note |

### Detailed checklist  every item to cover

- Register a normal user, then attempt to add 'role':'admin' in the body is it honoured? (B-02)

- Attempt mass-assignment of other unexpected fields (is_verified, id, permissions).

- If a reset flow exists: inspect reset token strength, expiry, single-use, and whether it leaks account existence.

- SQLi on login and register fields via sqlmap and manual payloads.

- Malformed input: missing fields, wrong types, oversized strings, unicode/emoji, null bytes.

- Duplicate registration / email reuse handling; user enumeration on register.

- Password rules enforced (length, complexity) try weak passwords like '123'.

- Identify hashing (bcrypt/argon2 vs plaintext/MD5) and confirm the work factor is adequate.

- Confirm passwords/secrets are never logged during registration or reset.

- Rate limiting on registration and reset (spam / abuse).

### Deliverables & Acceptance

- Registration findings - B-02 status + any new registration issues.

- Password-reset findings - reset-token security (if the flow exists).

- Input-validation report - injection & malformed-input results with evidence.

- Password handling note - policy, hashing, storage assessment.

# Week 5  RBAC Model & Authorization Enforcement

Build the authoritative role→permission matrix and verify the middleware enforces it on every protected route.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Muath | Build the full RBAC matrix: every role × every protected route (allow/deny) from code, then verify each cell by testing. | RBAC matrix (verified) |
| Saad | Route-guard coverage: confirm every sensitive route is behind the auth middleware; find any unguarded routes. | Guard-coverage report |
| Himanshu | Middleware logic review: how role is read (token vs DB), fail-open vs fail-closed, consistency across services; formally log B-06. | Middleware review |
| Divjot | Review secure-config aspects of authorization: CORS, security headers, and any config that weakens access control; coordinate boundary with Jessica's team. | Auth config-hardening note |

### Detailed checklist  every item to cover

- Enumerate all roles (Admin, Analyst, End User, Ingestion Service) and all protected routes from the route files.

- For each role, authenticate and attempt every route; record actual allow/deny vs intended.

- Identify any route missing the auth/authorization middleware entirely (links to B-03).

- Determine the authorization source of truth: is 'role' trusted from the JWT alone, or re-checked against the DB?

- Fail-open test: send requests with missing/expired/garbage tokens is default-deny enforced?

- Check enforcement consistency between the API Gateway and the gRPC services.

- Confirm gRPC ports (50051/50053/50054) can't be called directly without auth from the host.

- Review CORS and security headers relevant to access control.

- Formally log B-06 (secrets in logs) with evidence.

### Deliverables & Acceptance

- RBAC matrix - verified role×route table, mismatches highlighted.

- Guard-coverage report - unprotected / inconsistent routes.

- Middleware review - how authorization decisions are made and where they're weak.

# Week 6  Privilege Escalation & Bypass Testing

Actively attempt to break the access-control model - the highest-value evidence in the review.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Muath | Vertical escalation: as end-user/analyst, attempt admin-only actions via forged/edited tokens and direct route calls. | Vertical-escalation findings |
| Saad | Horizontal escalation (IDOR): as one user, access another user's data by changing IDs/tokens. | Horizontal-escalation findings |
| Himanshu | Chain & bypass: combine weak-secret forging (W3) with RBAC gaps (W5); test gateway-bypass to gRPC services (B-03). | Escalation chain write-up |
| Divjot | Support evidence capture and reproduce findings independently to confirm they're reliable; start compiling the evidence appendix. | Verified evidence set |

### Detailed checklist  every item to cover

- Vertical: analyst token → call admin endpoints; expect deny.

- Vertical: forge a token with role=admin using the guessed secret; attempt admin actions.

- Horizontal/IDOR: request another user's records by changing user_id / resource id.

- Token substitution: use a valid low-priv token on high-priv routes.

- Direct-service access: hit user-service (50051) / ingestion (50053) / storage (50054) directly, bypassing gateway auth (B-03).

- Parameter tampering & forced browsing on protected routes.

- Re-test the unauthenticated ingestion endpoint (B-03) and document impact.

- Each successful escalation reproduced by a second team member for reliability.

- Full request/response evidence captured for every successful attempt.

### Deliverables & Acceptance

- Vertical & horizontal escalation findings - each with reproduction steps and evidence.

- Escalation chain write-up - how individual weaknesses combine into a full compromise path.

- Evidence appendix (draft) - organised proof for every finding so far.

# Week 7  Consolidation, Severity & Remediation

Turn raw findings into a clean, prioritised, remediation-ready set. No new testing unless verifying a fix.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Himanshu | Consolidate all findings; assign final severities; de-duplicate; map each to OWASP/CWE; write the executive summary. | Master findings register |
| Saad | Draft remediation for login/registration/reset findings (rate limiting, validation, secure reset tokens). | Remediation A |
| Muath | Draft remediation for RBAC/escalation findings (server-side role checks, default-deny, route guards). | Remediation B |
| Divjot | Draft remediation for dependency/config findings (exact upgrade targets, secret management, log hygiene); build the re-test checklist. | Remediation C + re-test list |

### Detailed checklist  every item to cover

- Every finding has: ID, title, description, steps, evidence, severity, OWASP/CWE, remediation, status.

- Findings sorted by severity; Critical/High summarised in an executive table.

- Cross-check nothing from the Week-1 inventory or Week-5 RBAC matrix is left untested.

- Remediation for each is concrete and specific (e.g., 'assign role server-side; ignore client role field').

- Secret-management recommendation (strong random secrets, rotation, keep out of logs & Git).

- Dependency remediation lists exact upgrade targets to clear the 11 npm vulns.

- Re-test checklist written so fixes can be verified next sprint.

- Lead sign-off on the full register.

### Deliverables & Acceptance

- Master findings register - the single source of truth, review-ready.

- Remediation plan - prioritised, actionable fixes mapped to findings.

- Executive summary - one page: risk posture + top issues.

# Week 8  Final Report & Showcase

Package everything into a professional deliverable and prepare the showcase presentation and demo.

### Tasks & Owners

| Owner | Task | Output |
| --- | --- | --- |
| Himanshu | Assemble the final vulnerability report (Part A format); build the showcase deck; assign speaking parts. | Final report + deck |
| Saad | Proof, format, and verify the evidence appendix; ensure every claim has a screenshot/log. | Evidence appendix |
| Muath | Prepare a live or recorded demo of the top escalation finding; rehearse. | Demo + rehearsal |
| Divjot | Compile the dependency/config section and the hand-off pack (fixes + re-test checklist) for the next sprint. | Hand-off pack |

### Detailed checklist  every item to cover

- Report contains: exec summary, methodology, scope, findings table, per-finding detail, remediation, appendix.

- Every finding traces to reproducible evidence in the appendix.

- Metrics summarised (e.g., X findings: n Critical / n High / n Medium / n Low) - mirrors Part A style.

- Standards references (OWASP/ASVS/CWE) cited throughout.

- Showcase deck: problem, what we did, key findings, demo, remediation, next steps.

- Dry-run the presentation; time it; assign each member a section.

- Hand-off pack finalised: what to fix, how to re-test, and current status of each finding.

### Deliverables & Acceptance

- Final vulnerability report - the primary graded deliverable.

- Showcase presentation - deck + demo, rehearsed.

- Hand-off pack - remediation + re-test checklist for the following sprint.

# 8. Progress Tracking & Governance

A single findings register is maintained throughout and reviewed at the weekly sync. This keeps the work auditable and ensures nothing is dropped before the project closes.

| ID | Area | Severity | Status | Owner / Notes |
| --- | --- | --- | --- | --- |
| AUTH-01 | e.g. weak JWT secret | Critical | Open | Himanshu |
| AUTH-02 | e.g. no login rate limit | High | In Progress | Saad |
| RBAC-01 | e.g. role trusted from token | High | Open | Muath |
| CFG-01 | e.g. vulnerable dependency | High | Open | Divjot |
| … | … | … | … | … |

## Weekly sync (standing agenda)

- Each member's progress vs the week's checklist.

- New findings logged and severities agreed.

- Blockers (missing accounts, backend changes) and who unblocks.

- Boundary check-in with the API-security sub-team.

- Confirm we're on the latest backend after any upstream change.

## Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Backend changes under us (active dev branch, other teams editing middleware). | Pin the tested commit/branch; note the version in every finding; pull latest and re-verify before the final report. |
| Overlap with 'Enhance API Security' sub-team. | Written scope boundary in Week 1; weekly check-in. |
| Missing role test accounts. | Request from backend lead in Week 1; create via registration if permitted. |
| Findings not reproducible later. | Capture raw request/response + screenshots at discovery; second member reproduces key findings. |
| New member ramp-up (Divjot). | Start on the self-contained config/dependency stream; beginner guide provided; pair on the first setup. |
| Running out of time before close. | Front-load testing (Weeks 2-6); consolidation and report reserved for Weeks 7-8; weekly tracking prevents slippage. |